## Action plan format
MFG2 Mold Chie-Tech Automation Action Plan
[5 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
Project Name | Sub-Job | Respond | Action Process |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 |  |  | 1.Kaizen Sheet. -Confirm user require / merit | Plan
Actual
|  |  | 2.Design concept. -Design --> User/QA Chk --> Safety Chk | Plan
Actual
|  |  | 3.Order Part/Equipment -Confirm cost / budget --> Order | Plan
Actual
|  |  | 4.Making -Making Unit,Main body / Software | Plan
Actual
|  |  | 5.Trial / Debug -User/QA Chk --> Safety Chk | Plan
Actual
|  |  | 6.Preparation for Start Use -D/S,Process change approved -Prepare all STD.,TPM/Training | Plan
Actual
|  |  | 7.Start Use -Check performance / CPK --> Safety Chk | Plan
Actual
2 |  |  | 1.Kaizen Sheet. -Confirm user require / merit | Plan
Actual
|  |  | 2.Design concept. -Design --> User/QA Chk --> Safety Chk | Plan
Actual
|  |  | 3.Order Part/Equipment -Confirm cost / budget --> Order | Plan
Actual
|  |  | 4.Making -Making Unit,Main body / Sofeware | Plan
Actual
|  |  | 5.Trial / Debug -User/QA Chk --> Safety Chk | Plan
Actual
|  |  | 6.Preparation for Start Use -D/S,Process change approved -Prepare all STD.,TPM/Training | Plan
Actual
|  |  | 7.Start Use -Check performance / CPK | Plan
Actual

## Chie-Tech HT_mold
2025 Chie-Tech Progressive | [9 empty] | E-J1 | 235000 |  | Baht/Y
Update : | 2025-07-01
Current accumulate result | [7 empty] | Monthly
|  | Plan |  | Actual |  |  |  | Plan |  | Actual
Chie-tech QTY |  | 14 |  | 10 |  | Item |  | 3 |  | 1 |  | Item
Katsu-jin |  | 2.531 |  | 2.151 |  | Person |  | 0.49 |  | 0.2 |  | Person
Cost down |  | 594.785 |  | 505.485 |  | K.Baht |  | 115.15 |  | 47 |  | K.Baht
Unit : Item
QTY (Items) |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Plan | QTY | 0 | 2 | 2 | 1 | 3 | 3 | 3 | 0 | 4 | 3 | 2 | 2
| Accumulate | 0 | 2 | 4 | 5 | 8 | 11 | 14 | 14 | 18 | 21 | 23 | 25
Actual | QTY | 0 | 2 | 2 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Accumulate | 0 | 2 | 4 | 5 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10
Unit : Person
Katsu Jin (Person) |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Plan | QTY | 0 | 0.2 | 0.3 | 1 | 0.301 | 0.24 | 0.49 | 0 | 2.3 | 0.8 | 1.9 | 0.6
| Accumulate | 0 | 0.2 | 0.5 | 1.5 | 1.801 | 2.041 | 2.531 | 2.531 | 4.831 | 5.631 | 7.531 | 8.131
Actual | QTY | 0 | 0.2 | 0.3 | 1 | 0.211 | 0.24 | 0.2 | 0 | 0 | 0 | 0 | 0
| Accumulate | 0 | 0.2 | 0.5 | 1.5 | 1.711 | 1.951 | 2.151 | 2.151 | 2.151 | 2.151 | 2.151 | 2.151
|  | 2025-12-01: Unit : K.Baht | [10 empty] | Name | Total | Finished
Cost down merit (K.Baht) |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | [10 empty] | Phongsakon | 9 | 2
Plan | QTY | 0 | 47 | 70.5 | 235 | 70.735 | 56.4 | 115.15 | 0 | 540.5 | 188 | 446.5 | 141 | [10 empty] | Sujittra | 7 | 2
| Accumulate | 0 | 47 | 117.5 | 352.5 | 423.235 | 479.635 | 594.785 | 594.785 | 1135.285 | 1323.285 | 1769.785 | 1910.785 | [10 empty] | Thanaseth | 1 | 1
Actual | QTY | 0 | 47 | 70.5 | 235 | 49.585 | 56.4 | 47 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Sontaya | 1 | 1
| Accumulate | 0 | 47 | 117.5 | 352.5 | 402.085 | 458.485 | 505.485 | 505.485 | 505.485 | 505.485 | 505.485 | 505.485 | [10 empty] | Phuripat | 3 | 0
Chie-Tech List Progressive | bar: 2025-01-01 to 2025-03-01
Chie-Tech List | Project |  |  |  | Respond |  |  |  | Estimate cost | Katsu-Jin | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
1 | Material check Temp. sensor |  |  |  | Phongsakon |  | Plan |  |  | 0.2 | [12 empty] | 1 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0.2 | [12 empty] | 1 | bar: 2025-01-01 to 2025-12-01
2 | Jig check EP mold cassette |  |  |  | Thanaseth |  | Plan |  |  | 0 | [12 empty] | 1 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0 | [12 empty] | 1 | Monthly progressive |  |  | Plan Project | Actual Project | Acc Plan | Acc Actual | Plan Katsu-Jin | Actual Katsu-Jin | Acc.Plan | Acc. Actual | Phongsakon | Sujittra | bar: 2025-01-01 to 2025-12-01
3 | Auto cut off material |  |  |  | Phongsakon |  | Plan |  |  | 0.2 | [12 empty] | 1 | 2025-01-01 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0.2 | [12 empty] | 1 | 2025-02-01 |  |  | 2 | 2 | 2 | 2 | 0.2 | 0.2 | 0.2 | 0.2 | 1 | 0 | bar: 2025-01-01 to 2025-12-01
4 | Combine line 33S , 32S , 312S |  |  |  | Sujittra |  | Plan |  |  | 1 | [12 empty] | 1 | 2025-03-01 |  |  | 2 | 2 | 4 | 4 | 0.3 | 0.3 | 0.5 | 0.5 | 1 | 0 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 1 | [12 empty] | 1 | 2025-04-01 |  |  | 1 | 1 | 5 | 5 | 1 | 1 | 1.5 | 1.5 | 0 | 1 | bar: 2025-01-01 to 2025-12-01
5 | Purge material pressing machine No.2 |  |  |  | Sujittra |  | Plan |  |  | 0.2 | [12 empty] | 1 | 2025-05-01 |  |  | 3 | 3 | 8 | 8 | 0.301 | 0.211 | 1.801 | 1.711 | 1 | 1 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0.2 | [12 empty] | 1 | 2025-06-01 |  |  | 2 | 2 | 10 | 10 | 0.24 | 0.24 | 2.041 | 1.951 | 0 | 2 | bar: 2025-01-01 to 2025-12-01
6 | Sensor check lock Daisha |  |  |  | Phuripat |  | Plan |  |  | 0.001 | [13 empty] | 2025-07-01 |  |  | 3 | 1 | 13 | 11 | 0.49 | 0.04 | 2.531 | 1.991 | 1 | 0 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0.001 | [13 empty] | 2025-08-01 |  |  | 0 | 0 | 13 | 11 | 0 | 0 | 2.531 | 1.991 | 0 | 0 | bar: 2025-01-01 to 2025-12-01
7 | Cutting gate auto FE2-L232 |  |  |  | Sujittra |  | Plan |  |  | 0.1 | [12 empty] | 1 | 2025-09-01 |  |  | 4 | 0 | 17 | 11 | 2.3 | 0 | 4.831 | 1.991 | 1 | 0 | bar: 2025-01-01 to 2025-12-01
[7 empty] | Actual |  |  | 0.01 | [12 empty] | 1 | 2025-10-01 |  |  | 3 | 0 | 20 | 11 | 0.8 | 0 | 5.631 | 1.991 | 2 | 1 | bar: 2025-01-01 to 2025-12-01
8 | Water Temp & Flow rate sensor No.2 |  |  |  | Phongsakon |  | Plan |  |  | 0.2 | [12 empty] | 1 | 2025-11-01 |  |  | 2 | 0 | 22 | 11 | 1.9 | 0 | 7.531 | 1.991 | 1 | 0 | bar: 2025-07-01; 2025-09-01
[7 empty] | Actual | [15 empty] | 1 | 2025-12-01 |  |  | 2 | 0 | 24 | 11 | 0.6 | 0 | 8.131 | 1.991 | 2 | 0
| Bari vacuum machine |  |  |  | Sujittra |  | Plan | [15 empty] | 1 | Sum |  |  | 24 | 11
[7 empty] | Actual | [15 empty] | 1
9 | Automation combine cell |  |  |  | Phongsakon |  | Plan |  |  | 0.2 | [12 empty] | 1 | bar: 2025-12-01
[7 empty] | Actual | [15 empty] | 1 | Expand project |  |  | Katsu jin | Jul | Aug | Sep | Oct | Nov | Dec
10 | Purge material pressing machine No.3 |  |  |  | Sujittra |  | Plan |  |  | 0.2 | [9 empty] | 1 |  |  | 1 | Cut off |  |  | Item | 7 | 7 | 7 | 7 | 7 | 8
[7 empty] | Actual | [15 empty] | 1 |  |  |  | 0.2 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.6
11 | Auto Production Step2 |  |  |  | Phongsakon |  | Plan |  |  | 1.6 | [10 empty] | 1 |  | 1 | Check Temp.and Humidity |  |  | Item | 7 | 7 | 7 | 7 | 7 | 8
[7 empty] | Actual | [15 empty] | 1 |  |  |  | 0.2 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.6
12 | Auto Print screen |  |  |  | Phongsakon |  | Plan |  |  | 0.4 | [11 empty] | 1 | 1 |  |  |  |  | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 3.2
[7 empty] | Actual | [15 empty] | 1 |  |  |  |  | Oct: Total Katsu-Jin; Dec: 17.2
13 | Auto flow rate Check Spot Welding | [5 empty] | Plan | [15 empty] | 1
[7 empty] | Actual | [15 empty] | 1
14 | Free air Compressor System |  |  |  | Phongsakon |  | Plan |  |  | 0.5 | [9 empty] | 1 |  |  | 1
[7 empty] | Actual | [15 empty] | 1
15 | Auto count Part |  |  |  | Phongsakon |  | Plan |  |  | 0.2 |  |  |  |  | 1 | [7 empty] | 1
[7 empty] | Actual |  |  | 0.2 |  |  |  |  | 1 | [7 empty] | 1
16 | Auto cutting pom |  |  |  | Wilai / Sonetaya |  | Plan |  |  | 0.25 | [6 empty] | 1 | [5 empty] | 1
[7 empty] | Actual | [15 empty] | 1
17 | Auto Drain water Mold |  |  |  | Phuripat |  | Plan |  |  | 0.1 | [8 empty] | 1 |  |  |  | 1
[7 empty] | Actual | [15 empty] | 1
18 | Dot Auto Part |  |  |  | Phongsakon |  | Plan |  |  | 0.1 | [9 empty] | 1 |  |  | 1
[7 empty] | Actual | [15 empty] | 1
19 | Auto load material 2nd inj. unit |  |  |  | Phuripat |  | Plan |  |  | 0.3 | [10 empty] | 1 |  | 1
[7 empty] | Actual | [15 empty] | 1
20 | Jig Flip Part QC5-1906 |  |  |  | Sontaya |  | Plan |  |  | 0.1 |  |  | 1 | [9 empty] | 1
[7 empty] | Actual |  |  | 0.1 |  |  | 1 | [9 empty] | 1
21 | Jig sticking film QC7-8139 |  |  |  | Sujittra |  | Plan |  |  | 0.04 | [5 empty] | 1 | [6 empty] | 1
[7 empty] | Actual |  |  | 0.04 | [5 empty] | 1 | [6 empty] | 1
22 | Jig sticking film QC9-1762 |  |  |  | Sujittra |  | Plan |  |  | 0.04 | [6 empty] | 1
[7 empty] | Actual |  |  | 0.04 | [6 empty] | 1
23 | TSS alarm status Machine |  |  |  | Phongsakon |  | Plan |  |  | 1 | [8 empty] | 1
Actual
24 | Auto cut off material |  |  |  | Phongsakon |  | Plan |  |  | 1 | Expand 5 m/c | [7 empty] | 1
Actual
25 | Material check Temp. sensor |  |  |  | Phongsakon |  | Plan |  |  | 1 | Expand 5 m/c
Actual
25 | [6 empty] | Plan
Actual
26 | [6 empty] | Plan
Actual
27 | [6 empty] | Plan
Actual
28 | [6 empty] | Plan
Actual
29 | [6 empty] | Plan
Actual
30 | [6 empty] | Plan
Actual
Chie-Tech List | Project |  |  |  | Respond |  |  | Katsu-Jin | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
1 | Material check Temp. sensor |  |  |  | Phongsakon |  | Plan | 0.2
[7 empty] | Actual | 0.2
2 | Jig check EP mold cassette |  |  |  | Thanaseth |  | Plan | 0
[7 empty] | Actual | 0
3 | Auto cut off material |  |  |  | Phongsakon |  | Plan | 0.2
[7 empty] | Actual | 0.2
4 | Combine line 33S , 32S , 312S |  |  |  | Sujittra |  | Plan | 1
[7 empty] | Actual | 1
5 | Purge material pressing machine No.2 |  |  |  | Sujittra |  | Plan | 0.2
Actual
6 | Cutting gate auto FE2-L232 |  |  |  | Sujittra |  | Plan | 0.1
Actual
7 | Water Temp & Flow rate sensor No.2 |  |  |  | Phongsakon |  | Plan | 0.2
Actual
8 | Bari vacuum machine |  |  |  | Sujittra |  | Plan | 0.1
Actual
9 | Jig Flip Part QC5-1906 |  |  |  | Sontaya |  | Plan | 0.1
Actual
10 | Auto count Part |  |  |  | Phongsakon |  | Plan | 0.2
Actual
12 | Auto Print screen |  |  |  | Phongsakon |  | Plan | 0.4
Actual
13 | Automation combine cell |  |  |  | Phongsakon |  | Plan | 0.1
Actual
14 | Free air Compressor System |  |  |  | Phongsakon |  | Plan | 0.5
Actual
15 | Purge material pressing machine No.3 |  |  |  | Sujittra |  | Plan | 0.2
Actual
16 | Auto cutting pom |  |  |  | Sujittra |  | Plan | 0.25
Actual
17 | Auto Drain water Mold |  |  |  | Phongsakon |  | Plan | 0.1
[5 empty] | Phuripat |  | Actual
18 | Dot Auto Part |  |  |  | Phongsakon |  | Plan | 0.1
Actual
19 | Auto load material 2nd inj. unit |  |  |  | Sujittra |  | Plan | 0.37
Actual
20 | Auto Production Step2 |  |  |  | Phongsakon |  | Plan | 2
[7 empty] | Actual | 0.1
Items
Month
Items
Items
Months
Persons
Months
Pers
Month
Design concept
Kaizen Sheet
Order
Making
Trial
Start use
Start use
Start use
Start use
Start use
Wait MP
Start use
Making
Trial
Start use
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
PLAN
Order
Making
Start use
Order
Making
Start use
Start use
Making
Order
Kaizen Sheet
Design concept
Note on R48: MR.THAMMAPHON CHANTASIRIWATE: Change from May
Note on S54: MR.THAMMAPHON CHANTASIRIWATE: Slide from Jun
Note on U54: wait spare
Note on T56: MR.THAMMAPHON CHANTASIRIWATE: Change from Jul
Note on X58: MR.THAMMAPHON CHANTASIRIWATE: Slide from Nov
Note on T68: MR.THAMMAPHON CHANTASIRIWATE: Change from Sep
Note on V68: MR.THAMMAPHON CHANTASIRIWATE: Slide from Aug
Note on U78: MR.THAMMAPHON CHANTASIRIWATE: Change from Aug
Note on W78: MR.THAMMAPHON CHANTASIRIWATE: Change from Sep

## Chie tech
2025 MFG.2 Mold Chie-tech Activity | [5 empty] | Update : | 2025-07-01 |  |  |  | E-J1 | 235000 |  | Baht/Y
Detail |  | Current | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Chie Tech | Plan Item. | 3 | 0 | 2 | 2 | 1 | 3 | 3 | 3 | 0 | 4 | 3 | 2 | 2
| Actual Item. | 1 | 0 | 2 | 2 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Acc Plan Item. | 14 | 0 | 2 | 4 | 5 | 8 | 11 | 14 | 14 | 18 | 21 | 23 | 25
| Acc Act. Item. | 10 | 0 | 2 | 4 | 5 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10
Katsu Jin | Plan Per. | 0.49 | 0 | 0.2 | 0.3 | 1 | 0.301 | 0.24 | 0.49 | 0 | 2.3 | 0.8 | 1.9 | 0.6
| Actual Per. | 0.2 | 0 | 0.2 | 0.3 | 1 | 0.211 | 0.24 | 0.2 | 0 | 0 | 0 | 0 | 0
| Acc Plan Per. | 2.531 | 0 | 0.2 | 0.5 | 1.5 | 1.801 | 2.041 | 2.531 | 2.531 | 4.831 | 5.631 | 7.531 | 8.131
| Acc Act. Per. | 2.151 | 0 | 0.2 | 0.5 | 1.5 | 1.711 | 1.951 | 2.151 | 2.151 | 2.151 | 2.151 | 2.151 | 2.151
Success rate
Items
Currency | 55.56%
Yearly | 40%
Katsu jin
Currency | 44.52%
Yearly | 26.45%
Cost down | 505485
ACTIVITY CHIE-TECH & AUTOMATION
PLAN FOLLOW UP
Y'25 Target


## Automation
2025 Factory Automation Activity | [10 empty] | E-J1 | 235000 |  | Baht/Y
Detail |  | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FA | Plan Item. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0
| Plan revise_01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Item. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acc Plan Item. |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Acc Act. Item. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sho Jin | Plan Per. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0
| Plan revise_01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Per. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acc Plan Per. |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Acc Act. Per. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
19583.3333
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Jul: 0; Aug: 0; Sep: 0; Oct: 0; Nov: 0; Dec: 0 | 0
900000
4

## Progressive WG
Progressive Work Group
No. | PIC | Target Katsu-Jin | Plan Katsu Jin | Accum. Katsu Jin | Project Name | Estimate Katsu-Jin | Actual Katsu-Jin | Plan Finished | Responds | Status
1 | ADM Planner | 1 | 0
2 | ADM Material | 1 | 0
3 | ADM Store | 1 | 0.47 |  | Bari vacum cleaner | 0.07 |  |  | Namfon
[5 empty] | Auto count part | 0.4 |  |  | Namfon |  | 0.62
4 | Production | 1 | 0.62 | 0 | Auto load material 2nd inj.unit | 0.37 |  |  | Mr.somruck
[5 empty] | Auto cutting Pom | 0.25 |  |  | Mr.somruck
5 | Mold | 1 | 0 |  | Jig Check EP Cassette | 0.0005 | 0.0005 | Feb | Thanaseth | Finished
6 | Machine | 1 | 0
7 | New Model | 1 | 0
8 | QA | 1 | 0
| Total | 8 | 1.09 |  |  | 1.0905 | 0.0005

## Action Plan 1st Half
Chie-Tech List
NO | Project | Respond |  | Katsu-Jin | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Material check Temp. sensor | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
2 | Jig check EP mold cassette | Thanaseth | Plan | 0
|  |  | Actual | 0
3 | Auto cut off material | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
4 | Jig Flip Part QC5-1906 | Sontaya | Plan | 0.1
|  |  | Actual | 0.1
5 | Combine line 33S , 32S , 312S | Sujittra | Plan | 1
|  |  | Actual | 1
6 | Cutting gate auto FE2-L232 | Sujittra | Plan | 0.1
|  |  | Actual | 0.01
7 | Auto count Part | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
8 | Sensor Check Lock Daisha | Phuripat | Plan | 0.1
|  | Phuripat | Actual | 0.1
9 | Purge material pressing machine No.2 | Sujittra | Plan | 0.2
Actual
10 | Water Temp & Flow rate sensor No.2 | Phongsakon | Plan | 0.25
Actual
11 | Auto cutting pom | Sujittra | Plan | 0.1
Actual
12 | Auto Production Step2 | Phongsakon | Plan | 1.6
|  |  | Actual | 1.6
13 | Bari vacuum machine | Sujittra | Plan | 0.1
Actual
14 | Free air Compressor System | Phongsakon | Plan | 0.5
Actual
15 | Auto Drain water Mold | Phuripat | Plan | 0.1
|  | Phuripat | Actual
16 | Purge material pressing machine No.3 | Sujittra | Plan | 0.2
Actual
17 | Dot Auto Part | Phongsakon | Plan | 0.1
Actual
18 | Automation combine cell | Phongsakon | Plan | 0.2
Actual
19 | Auto load material 2nd inj. unit | Sujittra | Plan | 0.3
Actual
20 | Auto Print screen | Phongsakon | Plan | 0.4
Actual
21 |  |  | Plan
Actual
22 |  |  | Plan
Actual
23 |  |  | Plan
Actual
24 |  |  | Plan
Actual
25 |  |  | Plan
Actual
26 |  |  | Plan
Actual
Debug
Making
Order
Debug
Making
Order
Debug
Design concept
Kaizen Sheet
Order
Making
Trial
Start Use
Design
Design
Order
Order
Making
Making
Design
Design
Order
Order
Making
Making
Design
Design
Order
Order
Making
Making
Design
Design
Making
Making
Design
Design
Making
Making
Making Y'24
Making Y'24
Debug
Debug
Debug
Debug
Debug
Debug
Debug
Design
Making
Debug
Order
Design
Making
Order
Debug
Order
Making
Debug
Order
Design
Making
Debug
Order
Making
Design
Making
Design
Cylinder Long L/T order
Design
Design
Design
Order
Debug
Order
Making
Design
Debug
Order
Making
Design
Design
Order
Making
Debug
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Equipment Budget
Order
Making
Debug

## Action Plan 2nd Half
Chie-Tech List
NO | Project | Respond |  | Katsu-Jin | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Material check Temp. sensor | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
2 | Jig check EP mold cassette | Thanaseth | Plan | 0
|  |  | Actual | 0
3 | Auto cut off material | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
4 | Jig Flip Part QC5-1906 | Sontaya | Plan | 0.1
|  |  | Actual | 0.1
5 | Combine line 33S , 32S , 312S | Sujittra | Plan | 1
|  |  | Actual | 1
6 | Cutting gate auto FE2-L232 | Sujittra | Plan | 0.1
|  |  | Actual | 0.01
7 | Auto count Part | Phongsakon | Plan | 0.2
|  |  | Actual | 0.2
8 | Sensor Check Lock Daisha | Phuripat | Plan | 0.1
|  | Phuripat | Actual | 0.1
9 | Purge material pressing machine No.2 | Sujittra | Plan | 0.2
Actual
11 | Jig sticking film QC9-1762 | Sujittra | Plan | 0.04
Actual
12 | Auto cutting pom | Phuripat | Plan | 0.1
Actual
13 | Water Temp & Flow rate sensor No.2 | Phongsakon | Plan | 0.25
Actual
14 | Auto Production Step2 | Phongsakon | Plan | 1 | bar: Jan W1 to Apr W4
Actual | bar: Jan W1 to Apr W4
15 | Bari vacuum machine | Sujittra | Plan
Actual
16 | Free air Compressor System | Phongsakon | Plan | 0.5
Actual
17 | Auto Drain water Mold | Phuripat | Plan | 0.1
|  | Phuripat | Actual
18 | Purge material pressing machine No.3 | Phuripat | Plan | 0.2
Actual
19 | Dot Auto Part | Phongsakon | Plan | 0.1
Actual
20 | Automation combine cell | Phongsakon | Plan | 0.2
Actual
21 | Auto load material 2nd inj. unit | Phuripat | Plan | 0.3
Actual
22 | Auto Print screen | Phongsakon | Plan | 0.4
Actual
23 | TSS alarm status Machine | Phongsakon | Plan | 1
Actual
24 | Material check Temp. sensor | Phongsakon | Plan | 1
Actual
25 | Auto cut off material | Phongsakon | Plan | 1
Actual
26 | Auto cutting Gate QC9-1814-000/QC9-1815-000 | Phongsakon | Plan
Actual
27 | Box Lode Material | Phongsakon | Plan
Actual
28 | Material Purge Mold Size(60x100x30) | Phuripat | Plan | bar: Jul W1
Actual
29 | Material Purge Mold Size(105x105x30) | Phuripat | Plan
Actual
30 | Material Purge Mold Size(25x27x30) | Phuripat | Plan
Actual
31 | Material Purge Mold Size(110x130x15) | Phuripat | Plan
Actual
32 | Material Purge Mold Size(60x210x35) | Phuripat | Plan
Actual
Order
Debug
Making
Order
Design concept
Kaizen Sheet
Order
Making
Trial
Start Use
Design
Design
Debug
Order
Making
Design
Design
Order
Making
Debug
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Equipment Budget
Order
Making
Debug
Design
Order
Making
Design
Order
Making
Design
Order
Order
Making
Debug
Order
Order
Making
Delay wait water tube
New plan Jul
Design
Order
Making
Debug
Design
Order
Making
Debug
Design
Order
Making
Debug
Making
Debug
Making
waiting OHS confirm manual
waiting OHS confirm manual
Solenoid valve will arrive 22/8
Confirm User then order parts
Order Delay
Design
Order
Making
Debug
Design
Order
Making
Debug
Expand Project
New Project
Expand Project
Aug Sent for Job request POM reuse All Result OK

## Sheet1
MONTH | SUBJECT | DX | CT | FA | SHOU JIN | KATSU JIN | TARGET | ACTUAL | REMARK
JAN | [6 empty] | 0 | 0
FEB | Material check Temp. sensor |  | 0.2 |  |  | 0.2 | 0.2 | 0.2
| Jig check EP mold cassette |  |  |  |  | 0 | 0 | 0 | For Easy working
MAR | Auto cut off material |  | 0.2 |  |  | 0.2 | 0.2 | 0.2
| Jig Flip Part QC5-1906 |  | 0.1 |  |  | 0.1 | 0.1 | 0.1
APR | Combine line 33J , 32J , 312J |  | 1 |  |  | 1 | 1 | 1
May | Sensor Lock Daisha |  | 0.001 |  |  | 0.001 | 0.001 | 0.001
| Cutting gate auto FE2-L232 |  | 0.1 |  |  | 0.1 | 0.1 | 0.01
| Auto count Part |  | 0.2 |  |  | 0.2 | 0.2 | 0.2
JUN | Purge material pressing machine No.2 |  | 0.2 |  |  | 0.2 | 0.2 | 0.2
| Jig sticking Film QC7-8139 |  | 0.04 |  |  | 0.04 | 0.04 | 0.04 | Add
JUL | Water Temp & Flow rate sensor No.2 |  | 0.2 |  |  | 0.2 | 0.2 |  | Slide plan from Jun
| Auto cutting POM |  | 0.25 |  |  | 0.25 | 0.25
| Jig sticking Film QC9-1762 |  | 0.04 |  |  | 0.04 | 0.04
AUG | Bari vacuum machine | [7 empty] | Cancel
| TSS alarm status machine |  | 0.1 |  |  | 0.1 | 0.1
SEP | Expand Auto Cut off Material |  | 1 | [5 empty] | Expand = 5 M/C
| Expand Box Check Temp. & Him. |  | 1 | [5 empty] | Expand = 5 M/C
| Auto Drain water Mold |  | 0.1 |  |  | 0.1 | 0.1
OCT | Purge material pressing machine No.3 |  | 0.2 |  |  | 0.2 | 0.2
| Dot Auto Part |  | 0.1 |  |  | 0.1 | 0.1
| Free air Compressor System |  | 0.5 |  |  | 0.5 | 0.5 |  | Slide plan from Aug
NOV | Automation combine cell |  | 0.2 |  |  | 0.2 | 0.2
| Full Auto Production Step2 |  |  | 1.6 | 1 | 0.6 | 1.6
DEC | Auto Load 2nd Material |  | 0.3 |  |  | 0.3 | 0.3
| Auto Print screen |  | 0.4 |  |  | 0.4 | 0.4
| TOTAL | 0 | 6.431 | 1.6 | 1 | 5.031 | 6.031 | 1.951
plan
MONTH | SUBJECT | DX | CT | FA | SHOU JIN | KATSU JIN | TARGET | ACTUAL | REMARK
JAN | [7 empty] | 0
FEB | 1.CHIE-TECH (2 items) |  | 0.2 |  |  | 0.2 | 0.2 | 0.2
MAR | 1.CHIE-TECH (1 items) |  | 0.2 |  |  | 0.2 | 0.2 | 0.3
APR | 1.CHIE-TECH (2 items) |  | 1.1 |  |  | 1.1 | 1.1 | 1
MAY | 1.CHIE-TECH (3 items) |  | 0.3 |  |  | 0.3 | 0.3 | 0.21
JUN | 1.AUTOMATION : SMART STORE OUT LFP
| 2.CHIE-TECH (2 items) |  | 0.4 |  |  | 0.4 | 0.4
JUL | 1.AUTOMATION : SMART STORE IN
| 2.CHIE-TECH (1 items) |  | 0.25 |  |  | 0.25 | 0.25
AUG | 1.CHIE-TECH (2 items) |  | 0.6 |  |  | 0.6 | 0.6
SEP | 1.CHIE-TECH (1 items) |  | 0.1 |  |  | 0.1 | 0.1
OCT | 1.CHIE-TECH (2 items) |  | 0.3 |  |  | 0.3 | 0.3
NOV | 1.FULL AUTOMATION SYSTEM |  |  | 1 | 1 |  | 1
| 2.CHIE-TECH (2 items) |  | 0.5 |  |  | 0.5 | 0.5
DEC | 1.CHIE-TECH (1 items) |  | 0.4 |  |  | 0.4 | 0.4
2.AUTOMATION : SMARTSTORE OUT LFP/IJ
| TOTAL | 0 | 4.35 | 1 | 1 | 4.35 | 5.35 | 1.71