## Slide 1
Rank | Activity | Plan Effective [ Month ] | Status [ items ] | Remark
D 0 - 25% (Design) | Purge material pressing machine No.3 Dot Auto Part Automation combine cell Auto load material 2nd inj. Unit Auto Print screen | Oct Oct Nov Nov Dec | 5 | 
C 26 - 50% (Concept) | Auto Production Step.2 | Nov | 1 | 
B 51% - 75% (Order) | Free Air compressor system Auto Drain Expand Auto Cut off Material Expand Box Check Temp. & Him. | Oct Sep Sep Sep | 4 | 
A 76 - 100% (Making) | Material check Temp. sensor Jig check EP mold cassette Auto cut off material Jig Flip Part QC5-1906 Combine line 33J Auto Count Part Auto cut Gate FE2-L232 Sensor check Lock Daisha Purge material pressing machine No.2 Jig sticking film QC7-8139 Water Temp & Flow rate sensor No.2 Jig cutting POM Jig sticking film QC9-1762 TSS alarm status Machine | Feb Feb Mar Mar Apr May May May June June June => Aug Sep Jul Aug | 11/14 | 
HT-Mold : Y’25 Chie-Tech / Automation summary
Summary status by Rank control
Chart: Progressive
| Over all | June | Jul
Target | 25 | 3 | 3
Actual | 11 | 2 | 1
Slide
Slide Plan 2 Items.

## Slide 2
HT-Mold : Y’25 DX-Automation SUMMARY
 | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TTL
TARGET | 0.00 | 0.20 | 0.30 | 1.00 | 0.30 | 0.24 | 0.49 | 0.10 | 0.10 | 0.80 | 1.90 | 0.60 | 6.03
ACTUAL | 0.00 | 0.20 | 0.30 | 0.1 | 0.21 | 0.24 | 0.2 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1.95
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Target | 0 | 0.2 | 0.3 | 1 | 0.3 | 0.24 | 0.49 | 0.1 | 0.1 | 0.8 | 1.9 | 0.6
Acutal | 0 | 0.2 | 0.3 | 1 | 0.21 | 0.24
Acc.Target | 0 | 0.2 | 0.5 | 1.5 | 1.8 | 2.04 | 2.53 | 2.63 | 2.73 | 3.53 | 5.43 | 6.03
Acc.Actual | 0 | 0.2 | 0.5 | 1.5 | 1.71 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95
Target 8.0 Per.
Chart: DX-Automation
| Target | Actaul
Series 1 | 4 | 0
Chart: Chic-Tech
| Target | Actaul
Series 1 | 25 | 11
[item]
[item]
[per]
2

## Slide 3
HT-MFG2 Y2025 DX-Automation : Example Chie-tech , Automation
3

## Slide 4
HT-MFG2 Y2025 DX-Automation : Example Chie-tech , Automation
 Katsu-Jin , Sho-Jin |  |  |  |  | 
Process |  | Manpower (Person / Shift) |  |  | 
 |  | Before |  | After | 
 |  | 1001T | 1002T | 1001T | 1002T
1 | Cutting Gate | 1 | 1 | 0.7 Katsu-JIN =0.3 | 0.7 Katsu-JIN =0.3
2 | Cut Bari |  |  |  | 
3 | Cleaning Oil |  |  |  | 
4 | PAD Printing | 1 | 1 |  | 
5 | Appearance Check |  |  | 1 (Sho-Jin = 1) | 
6 | Packing |  |  |  | 
Total |  | 4 |  | 2.4 | 
Merit | 
Sho-JIN | 1 Pers.
Katsu-JIN | 0.6 Pers.
Start Plan | Nov’25
HT-MOLD Full Automation 1000 Ton
4
 | Jul | Aug | Sep | Oct | Nov | Dec
Action plan
Equipment Budget
Order
Making
Debug
Finish
Wait Production Confirm Time Man Power

## Slide 5
HT-MFG2 Y2025 DX-Automation : Example Chie-tech , Automation
5
Update Project Material POM
1
2
3
4
Box for Support Material POM Request Size = 4 Size
1.Size 25 mm x 27mm x 30 mm
2.Size 105 mm x 105 mm x 30 mm
3.Size 103 mm x 133 mm x 30 mm
4.Size 60 mm x 100 mm x 30 mm
TDM Request Size 25 mm x 27mm x 30 mm
Send OK = 80 Pcs. = 2 Kg.
TDM Request Size 103 mm x 133 mm x 30 mm
= 20 Pcs. = 25 KG.
PDE Request Size 105 mm x 105 mm x 30 mm
Send OK = 3 Pcs. = 1 KG.
Reuse Material = 28 KG.

## Slide 6
APPENDIX

## Slide 7
Expand project | Katsu jin | Jul | Aug | Sep | Oct | Nov | Dec
Cut off material | Item | 7 | 7 | 7 | 7 | 7 | 8
 | 0.2 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.6
Check Temp. & Humidity | Item | 7 | 7 | 7 | 7 | 7 | 8
 | 0.2 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.6
 | Total | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 3.2
 |  |  |  |  | Total Katsu-Jin |  | 17.2
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Target | 0 | 0.2 | 0.2 | 1.1 | 0.7 | 0.32 | 1.1 | 0.5 | 0.3 | 0.3 | 2.2 | 1.4
Acutal | 0 | 0.2 | 0.3 | 1
Acc.Target | 0 | 0.2 | 0.4 | 1.5 | 2.2 | 2.52 | 3.62 | 4.12 | 4.42 | 4.72 | 6.92 | 8.32
Acc.Actual | 0 | 0.2 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Target 8.0 Per.
[per]